## Slide 1: Novaxovid – Initial Implementation
Extending the COVID-19 vaccine portfolio within the National Immunisation Programme

## Slide 2: Introduction
Purpose
To outline the proposed approach to provide the Novavax COVID-19 vaccine (Novaxovid) as an alternative for people who are:
    unable to be vaccinated with the Pfizer vaccine, especially those who are required to be vaccinated by the Vaccination Order or their employer; or
    those hesitant to take an mRNA vaccine.
Context
The COVID-19 Vaccine Immunisation Programme (the programme) made supply arrangements to procure four vaccines (Pfizer, Janssen, AstraZeneca and Novavax) to inoculate the population
The national roll-out has used Pfizer as the first line vaccine for the programme to date.
In July the programme sought advice from CV TAG for the use of Janssen following Medsafe approval. This advice was there was no indication for the widespread use of Janssen however it could be considered for individuals who Pfizer was not suitable.
Cabinet approved this direction for the use of Janssen, however at around the same time it became known that delivery would not be available until Q1 2022, hence the programme was directed to consider AstraZeneca as an alternative.
AstraZeneca was implemented on the 26th November. To date approximately 8000 doses have been administered.
On 4th February 2022 Medsafe granted provisional approval of the two-dose Novavax COVID-19 vaccine, Novaxovid.

## Slide 3: Current status
CV TAG have considered the vaccine and provided the following key recommendations:
  two doses of the Novavax vaccine, given at least 3 weeks apart, are required for a primary vaccination course.
  Novavax can be administered as part of a heterologous primary schedule to people who have received another COVID-19 vaccine as their first dose, and this should occur at least 28 days after the first dose of the other COVID-19 vaccine, to account for recommended intervals for other vaccine brands.
  there should be no upper limit on time since the first dose.
  administration of the Novavax vaccine as a second dose should occur at least 28 days after the most recent dose of another COVID-19 vaccine.
  CV-TAG noted that there is a potential for Novavax to be used as a booster dose in the context of Omicron, however, at this stage, they will continue to monitor the evidence on Novavax as a booster.
This advice is currently being incorporated into a decision to use paper to be considered by accountable Ministers before the end of the month.
IMAC have been commissioned to produce the necessary training materials
The required information technology changes are currently underway.

## Slide 4: Implementation considerations
Currently only approved for primary course use for people 18 years or over. Therefore up to 360,000 doses could be used from the available unvaccinated eligible population. The anticipated uptake therefore is expected to be small.
Current stage of programme focused on booster or paediatric vaccination, which may result in some providers being un-willing to adopt the vaccine
Booster or heterologous use is off label requiring a prescription to use.
Changes using an order in council (used to allow Pfizer boosters to be administered at a shorter interval from the primary course) will not be available for Novaxovid
Vaccine is supplied in 10 doses per vial, and does not require dilution. This represents a potential risk in coadministration settings, however the volumes do not support dedicated clinics.
There is potential to phase out AstraZeneca with Novaxovid becoming the programmes non mRMA alternative to Pfizer, however the lack of approval for boosters does not promote this approach now.
The primary care sector is currently significantly engaged in the wider COVID response.

## Slide 5: Proposed Initial Implementation
Consumer Access
From a consumer’s perspective, access to Novaxovid follows the AstraZeneca model as set out below
Consumers will be provided sufficient information to determine if they are eligible for Novaxovid. This information will be available to them by way of:
    Published information about the alternative vaccine on the Ministry’s website.
    Telehealth Services (Whakarongorau).
    Consultation with their medical practitioner. (free to the consumer)
A consumer can determine if they are eligible and book an appointment in a clinic that is enabled for delivery of Novaxovid using the Book My Vaccine site, or by calling Whakarongorau.
In addition to the BMV location map, the HealthPoint website will provide consumer information regarding clinics that administer Novavovid.
No ability to book a booster will be available on the BMV site. CIR will allow administration to be recorded on the chance that it is prescribed.
This process will enable an individual to be booked by another person to assist with access for those less able to self-serve.

## Slide 6: Proposed Initial Implementation (cont)
Delivery Settings
DHBs will establish a controlled number of sites that are enabled to safely administer Novaxovid.
Sites will not be restricted to a specific enrolled population.
The location and nature of the providers will be specifically designed to promote access and achieving equitable outcomes.
Each setting will require access to an authorised prescriber to allow for heterologous administration.
Logistics
Leverage existing network, albeit with more standard 2-8 degree cold-chain requirements
Available via the inventory portal
Expected distribution from DHL and HCL direct to the sites with a minimum 10 vial delivery size.
DHB Pharmacies (where used in the distribution model) are able to distribute a single vial.
High stock wastage is expected due to the demand uncertainty and expected low consumer volumes (AstraZeneca trending to 8% utilisation)

## Slide 7: Proposed Initial Implementation (cont)
Workforce
IMAC have been commissioned to prepare the necessary training collateral, and updates to the clinical guidance within the Immunisation Handbook.
Novaxovid can be administered by fully authorised or provisionally authorised vaccinators, who have completed the training module. This includes Pharmacist Vaccinators but not COVID-19 vaccinators working under supervision.
Proposed Timeline
Decision to use approved (End of February)
Product available in NZ (Early March – to be confirmed)
Technology changes deployed (10th March) (Confirming if bookings would be visible then)
IMAC Online Training available (14th March)
Book My Vaccine visible (1st April)
Launch (from 1st April, but bookings available no later than 4th April)